## Approved
Approved indicators
Project:
Date:
Project Progress Report number:
# | Description | Target | WP | Activity | Description
Outputs
RCO81 | Participations in joint actions across borders
RCO83 | Strategies and action plans jointly developed
RCO84 | Pilot actions developed jointly and implemented in projects
RCO 85 | Participations in joint training schemes
RCO 87 | Organisations cooperating across borders
RCO 116 | Jointly developed solutions
Results
RCR 79 | Joint strategies and action plans taken up by organisations
RCR 81 | Completions of joint training schemes
RCR 84 | Organisations cooperating across borders after project completion
RCR 104 | Solutions taken up or up-scaled by organisations

## Reported
Reported indicators
Project:
Date:
Project Progress Report number:
# | Description | Target | Previous Target | Reached | Total Target | Measurment Unit | Executed Percentage | PPR | WP | Activity | Description | Deliverable/output indicator evidence | File(s) in "documents" section*
| Outputs | [6 empty] | 2
RCO81 | Participations in joint actions across borders | 9.00 | 0.00 | 10.00 | 10.00 | participations | 111.11 % | 2 | 1 | 2 | 1-day transnational workshop between 4 pilot sites to exchange knowledge and test joint solutions, with experts and stakeholders. | Organisation and delivery of a 1-day transnational workshop with 10 participants in Bilbao, Spain Signed attendance list with names, organisations, and countries of participants Workshop agenda and programme Photos from the sessions and field visits Workshop report, including a summary of activities and confirmation of total number of participants | RCO81 – Transnational workshop Bilbao evidences_WP1.2_PPR1 (zip file)
RCO83 | Strategies and action plans jointly developed | 12.00 | 0.00 | 0.00 | 0.00 | strategy/action plan | 0.00 % | 2
RCO84 | Pilot actions developed jointly and implemented in projects | 3.00 | 0.00 | 0.00 | 0.00 | pilot actions | 0.00 % | 2
RCO 85 | Participations in joint training schemes | 0.00 | 0.00 | 0.00 | 0.00 | participations | 0.00 % | 2
RCO 87 | Organisations cooperating across borders | 24.00 | 0.00 | 12.00 | 12.00 | organizations | 50.00 % | 2 | 2 | 1 | Organisations formally cooperating in the project as partners and associated partners. | Partnership agreement | RCO87 – Partnership Agreement_WP2.1_PPR1 (PDF)
RCO 116 | Jointly developed solutions | 0.00 | 0.00 | 0.00 | 0.00 | solutions | 0.00 % | 2
| Results | [6 empty] | 2
RCR 79 | Joint strategies and action plans taken up by organisations | 12.00 | 0.00 | 0.00 | 0.00 | strategy/action plan | 0.00 % | 2
RCR 81 | Completions of joint training schemes | 0.00 | 0.00 | 0.00 | 0.00 | participants | 0.00 % | 2
RCR 84 | Organisations cooperating across borders after project completion | 50.00 | 0.00 | 0.00 | 0.00 | organisations | 0.00 % | 2
RCR 104 | Solutions taken up or up-scaled by organisations | 0.00 | 0.00 | 00.00 | 00.00 | solutions | 0.00 % | 2
# | Description | Target | Previous Target | Reached | Total Target | Measurment Unit | Executed Percentage | PPR | WP | Activity | Description | Deliverable/output indicator evidence | File(s) in "documents" section*
| Outputs | [6 empty] | 5
RCO81 | Participations in joint actions across borders | 9.00 | 10.00 | 0.00 | 10.00 | participations | 111.11 % | 5
RCO83 | Strategies and action plans jointly developed | 12.00 | 0.00 | 0.00 | 0.00 | strategy/action plan | 0.00 % | 5
RCO84 | Pilot actions developed jointly and implemented in projects | 3.00 | 0.00 | 0.00 | 0.00 | pilot actions | 0.00 % | 5
RCO 85 | Participations in joint training schemes | 0.00 | 0.00 | 0.00 | 0.00 | participations | 0.00 % | 5
RCO 87 | Organisations cooperating across borders | 24.00 | 12.00 | 00.00 | 12.00 | organizations | 50.00% | 5
RCO 116 | Jointly developed solutions | 0.00 | 0.00 | 0.00 | 0.00 | solutions | 0.00 % | 5
| Results | [6 empty] | 5
RCR 79 | Joint strategies and action plans taken up by organisations | 12.00 | 0.00 | 0.00 | 0.00 | strategy/action plan | 0.00 % | 5
RCR 81 | Completions of joint training schemes | 0.00 | 0.00 | 0.00 | 0.00 | participants | 0.00 % | 5
RCR 84 | Organisations cooperating across borders after project completion | 50.00 | 0.00 | 0.00 | 0.00 | organisations | 0.00 % | 5
RCR 104 | Solutions taken up or up-scaled by organisations | 0.00 | 0.00 | 00.00 | 00.00 | solutions | 0.00 % | 5
* File name: Output/Result indicator code – Document - WP/Act - PPRnº